NORTHSTAR RETAIL

Retail AI Enablement Proposal

A practical roadmap for customer service, store operations, and inventory decisions

| Prepared for: Northstar Retail Leadership Team | Planning horizon: 90-day pilot and scale recommendation |
| --- | --- |
| Prepared by: Strategy & Transformation Office | Decision requested: Approve discovery and pilot design |

# Executive context

Northstar Retail is evaluating targeted AI capabilities to improve customer responsiveness, simplify store-team work, and create more confident inventory decisions. This template is intentionally concise, evidence-led, and oriented toward measurable outcomes.

## Priority outcomes

Reduce time to resolve routine customer-service questions.

Give store teams clear, policy-aligned operational guidance.

Improve planner visibility into demand signals and inventory exceptions.

# 90-day roadmap

| Phase | Workstream | Success signal |
| --- | --- | --- |
| Weeks 1–3 | Map high-volume service, store, and planning decisions. | Prioritized use-case backlog and baseline metrics. |
| Weeks 4–7 | Prototype grounded assistant workflows with human review. | Pilot users complete tasks faster with documented controls. |
| Weeks 8–12 | Measure value, adoption, risk, and scale requirements. | Leadership decision on rollout investment and operating model. |

# Recommended pilot scope

Start with a small number of repeatable workflows where the business owner, source information, and success measures are already clear. The pilot should combine retrieval-grounded guidance with explicit human review for high-impact decisions.

## Design principles

Use approved internal knowledge alongside current external evidence.

Maintain citations, run records, and version history for every deliverable.

Design the experience for store and service teams, not only technical users.

Measure quality, adoption, time saved, and risk before scale-up.

# Decision checklist

Confirm one executive sponsor and accountable workflow owner.

Approve the pilot use cases, source systems, and review controls.

Set baseline metrics and a 90-day decision date.

# Template guidance

When using this file in Artifact Studio, ask the supervisor to retain the concise executive tone, navy-and-blue hierarchy, structured roadmap, and measurable-outcome framing. The generated DOCX and PPTX remain editable for review and iteration.